## Definition of done
Definition of done — six numeric gates
All six, or the sprint is not done. Each is measurable the day it is claimed, from a named surface. 'It looks right in DebugView' is not a gate.
ID | Gate | Target | Definition | Measured where | Value at audit | Value at signoff | Status
DOD-1 | Attribution coverage | ≥ 75% | Share of registration_completed carrying a resolvable channel — a UTM pair, gclid, or fbclid. Not Direct, not Unassigned. | PostHog · Growth dashboard tile 2 | 0% — event does not fire |  | Not started
DOD-2 | Meta Event Match Quality | ≥ 7.5 | EMQ on CompleteRegistration in Events Manager. Driven by hashed email + phone, _fbc, _fbp, IP, user agent on the server event. | Meta Events Manager | n/a — no server events |  | Not started
DOD-3 | Server-side coverage | ≥ 75% | Meta-recorded CompleteRegistration as a share of PostHog registration_completed over the same window. PostHog is the denominator. | Meta vs PostHog, same 7 days | undefined — both missing |  | Not started
DOD-4 | Deduplication accuracy | ± 2% | Pixel and CAPI must collapse to one conversion. Meta total may not exceed PostHog total by more than 2%. | Meta Events Manager | n/a |  | Not started
DOD-5 | LCP regression | ≤ +100 ms | Change in p75 LCP on any instrumented surface, 7 days of field data after release. Breach reverts the ticket. | PostHog $web_vitals · tile 10 | baseline 4461 ms app entry |  | Not started
DOD-6 | Data hygiene | 0 events | Stored events containing access_token, refresh_token or provider_token. Verified by the query that found them. | PostHog SQL | 49 / 49 / 42 |  | Not started

## Sprint board
Marketing & Growth sprint — board
46 points. NUR-00 is security and does not wait for the sprint. NUR-01 to NUR-05 stop active money loss; if the sprint is cut, it is cut after those.
ID | WS | Pri | Ticket | Where | Pts | Status | Owner | Notes
NUR-00 | Security | P0 | Strip auth fragments from PostHog URL properties | app.nursia.io SDK | 2 | Not started | App team | 49 events hold live tokens. Sanitise, purge, rotate. Today.
NUR-01 | W1 | P0 | Forward query params on all four redirect stubs | src/app/(funnel)/* | 4 | Not started |  | signup, login, exam, try. Must carry gbraid + wbraid too
NUR-02 | W2 | P0 | Define and emit registration_completed | app.nursia.io | 3 | Not started | App team | The target event. Exists nowhere today
NUR-03 | W2 | P0 | Re-point Ads primary conversion at a firing event | Google Ads | 2 | Not started |  | Smart Bidding optimising against zero
NUR-04 | W6 | P0 | Tag every Meta ad URL with utm_source + utm_medium | Ads Manager | 1 | Not started |  | GA4 ignores fbclid for channel
NUR-05 | W1 | P0 | Install posthog-js on nursia.io behind reverse proxy | src/app/layout.tsx | 3 | Not started |  | Unifies funnel. Must clear DOD-5
NUR-06 | W1 | P0 | Capture first-touch channel as person properties | src/lib/analytics.ts | 2 | Not started |  | Written once, never overwritten
NUR-07 | W3 | P0 | Generate and thread a shared event_id | src/lib/analytics.ts | 3 | Not started |  | Gates DOD-4
NUR-08 | W3 | P0 | Build /api/meta/capi route handler | src/app/api/meta/capi | 5 | Not started |  | Enrich IP + UA, forward _fbp/_fbc
NUR-09 | W3 | P0 | SHA-256 user-data hashing helper | src/lib/meta-capi.ts | 2 | Not started |  | Required to reach DOD-2
NUR-10 | W3 | P0 | Send CompleteRegistration via pixel and CAPI | both | 2 | Not started |  | Verify EMQ ≥ 7.5 before closing
NUR-11 | W3 | P1 | Evaluate PostHog Meta Ads CDP destination | PostHog | 2 | Not started |  | Spike. May remove most of NUR-08
NUR-12 | W4 | P1 | Emit question_answered in the app | app.nursia.io | 2 | Not started | App team | view_item/select_item are not equivalents
NUR-13 | W4 | P1 | Cumulative attempt counter with fired-once flag | app.nursia.io | 3 | Not started | App team | Cross-surface, per person
NUR-14 | W4 | P1 | Emit activated at the fifth attempt | app.nursia.io | 2 | Not started | App team | Once per person ever
NUR-15 | W4 | P1 | Emit practice_session_completed for drill + exam | app.nursia.io | 2 | Not started | App team | Unified high-intent signal
NUR-16 | W5 | P1 | Add step_index to onboarding events | app.nursia.io | 1 | Not started | App team | Else a 5-step funnel reads as 1 step
NUR-17 | W5 | P1 | Add login_failed with a reason property | app.nursia.io | 1 | Not started | App team | 101 viewed to 1 completed is unexplained
NUR-18 | W5 | P1 | Emit purchase with value and currency | app.nursia.io | 2 | Not started | App team | No ROAS computable until this exists
NUR-19 | W6 | P1 | PostHog dashboard — tiles 6 and 10 | PostHog 595036 | 1 | Not started |  | Buildable now on existing data
NUR-20 | W6 | P2 | PostHog dashboard — remaining nine tiles | PostHog 595036 | 3 | Not started |  | Growth — channel to activation
NUR-21 | Perf | P1 | Move the Clarity tag off beforeInteractive | src/app/layout.tsx | 1 | Not started |  | Blocks hydration today. Straight LCP win
NUR-22 | Perf | P2 | Establish the LCP baseline for nursia.io | PostHog | 1 | Not started |  | 7 days field vitals after NUR-05
NUR-23 | W6 | P2 | Verify all six gates and sign off | tracker | 2 | Not started |  | DOD-1 to DOD-6 from named surfaces
NUR-24 | W3 | P1 | Google Ads Offline Conversion Import for purchase | Google Ads API | 3 | Not started |  | Upload gclid/gbraid/wbraid + value. Not a container
NUR-25 | W3 | P1 | Send Meta Purchase through CAPI | src/app/api/meta/capi | 2 | Not started |  | value + currency, same event_id as PostHog
Total points
Points done
P0 points outstanding
Percent complete

## Area coverage
Analytics by area
Nine product areas, each with its own owner and its own gap. Status mirrors the rails in the PRD.
Area | Name | Host | Status | Instrumented today | To add | Owner
A | Acquisition & landing | nursia.io | Partial | GA4 + Meta Pixel | PostHog, tagged ad URLs | This repo + Ads
B | Content & guides | nursia.io | Instrumented | Full funnel in GA4 | Mirror to PostHog, Lead via CAPI | This repo
C | Registration (TARGET) | app.nursia.io | Unmeasured | Nothing | registration_completed + CompleteRegistration | App team
D | Login & returning | app.nursia.io | Partial | login_viewed 101, login_completed 1 | login_failed + reason, login_method | App team
E | Onboarding | app.nursia.io | Partial | step_viewed 26, completed 2 | step_index, step_name | App team
F | Practice & activation | both | Unmeasured | GA4 only, capped at FREE_PREVIEW=2 | question_answered in app, activated | App team
G | High intent | app.nursia.io | Unmeasured | Drill only, wrong domain | practice_session_completed | App team
H | Monetisation | app.nursia.io | Partial | subscription_page_viewed 8, paywall_dismissed 7 | purchase with value + currency | App team
I | Performance | both | Below budget | App vitals live, site uninstrumented | Vitals on nursia.io, CI budget | Both

## Event QA
Event QA matrix
Tick each column only after seeing the event in PostHog, GA4 DebugView and Meta Test Events. Status reflects the estate as audited on 11 Sep 2026, not intent.
Event | Meta standard | Host | Status | In GA4 | In PostHog | In CAPI | Note | Verified by / date
$pageview | PageView | app.nursia.io | Live | No | Yes | No | 1173 events, 23 people. Marketing site missing
$web_vitals | — | app.nursia.io | Live | No | Yes | No | 312 events. Powers DOD-5
guide_viewed | — | nursia.io | Live | Yes | No | No | GA4 only today
resource_offered | — | nursia.io | Live | Yes | No | No | Fires on visibility, not render
resource_clicked | Lead | nursia.io | Live | Yes | No | Pending NUR-08 | Only Meta signal with volume
question_answered | ViewContent | nursia.io | Partial | Yes | No | No | Capped at FREE_PREVIEW=2. Absent in app
registration_completed | CompleteRegistration | app.nursia.io | MISSING | No | No | Pending NUR-10 | THE TARGET EVENT. Exists nowhere
login_viewed | — | app.nursia.io | Live | No | Yes | No | 101 events
login_completed | — | app.nursia.io | Suspect | No | Yes | No | 1 event against 101 viewed
login_failed | — | app.nursia.io | MISSING | No | No | No | Needed to explain the gap above
onboarding_step_viewed | — | app.nursia.io | Partial | No | Yes | No | No step_index, so drop-off invisible
onboarding_completed | — | app.nursia.io | Live | No | Yes | No | 2 events
activated | Custom Activated | app.nursia.io | MISSING | No | No | Pending NUR-14 | 5th cumulative question, once per person
practice_session_completed | Custom HighIntent | app.nursia.io | MISSING | No | No | Pending NUR-15 | Unifies drill and exam
exam_selection_viewed | — | app.nursia.io | Live | No | Yes | No | 1 event
subscription_page_viewed | — | app.nursia.io | Live | No | Yes | No | 8 events
paywall_dismissed | — | app.nursia.io | Live | No | Yes | No | 7 events
purchase | Purchase | app.nursia.io | MISSING | No | No | Pending NUR-18 | No ROAS until this exists
sign_up (legacy) | CompleteRegistration | nursia.io | BROKEN | No | No | No | Unreachable — SignupForm never mounts
exam_completed (legacy) | — | nursia.io | BROKEN | No | No | No | Unreachable behind /exam stub

## PostHog install
PostHog on nursia.io — install spec
The single change that makes eight of the outcome rows answerable. The app already reports to project 595036; this side does not, so neither half can describe a whole customer. PH-03 and PH-10 are the two that fail quietly rather than loudly.
ID | Area | Step | Detail | Ticket | Status | Verified
PH-01 | Proxy | Add /ingest rewrites to next.config.ts | Two rules: /ingest/static/:path* to us-assets.i.posthog.com/static, /ingest/:path* to us.i.posthog.com. Separate hosts — merging them breaks the SDK bundle or the recorder | NUR-05 | Not started
PH-02 | Proxy | Set skipTrailingSlashRedirect: true | Next would otherwise redirect /ingest/decide/ to /ingest/decide and drop the POST body with it | NUR-05 | Not started
PH-03 | Init | api_host = '/ingest' | Same-origin. us.i.posthog.com is blocked far more on paid/mobile than organic desktop, which would bias the exact comparison the dashboard exists to make. DOD-3 depends on this | NUR-05 | Not started
PH-04 | Init | ui_host = 'https://us.posthog.com' | Where 'open in PostHog' links resolve. Without it they point at the proxy path and 404 | NUR-05 | Not started
PH-05 | Init | capture_pageview = 'history_change' | SDK watches the History API, so App Router navigation captures with no router subscription. The usePathname effect double-fires on first render and misses replaceState | NUR-05 | Not started
PH-06 | Init | person_profiles = 'identified_only' | Most marketing traffic never signs up. A profile per anonymous reader costs money and answers nothing | NUR-05 | Not started
PH-07 | Init | capture_performance = { web_vitals: true } | Field Core Web Vitals. DOD-5 is enforced against this rather than a Lighthouse run | NUR-05 | Not started
PH-08 | Init | defaults pinned to '2026-08-30' | Leaving defaults unset silently changes SDK behaviour on upgrade | NUR-05 | Not started
PH-09 | Attribution | Capture first touch with register_once | utm_source/medium/campaign/content/term, gclid, gbraid, wbraid, fbclid, src — prefixed initial_ | NUR-06 | Not started
PH-10 | Attribution | Do NOT use setPersonProperties for this | Under identified_only it either no-ops or creates the anonymous profile the setting exists to avoid. register_once gives first-touch-wins at the storage layer, survives to $identify, and costs no profile | NUR-06 | Not started
PH-11 | Events | Dual-send from the existing track() in analytics.ts | One edit sends all nine existing events. No change to any of the nine call sites | NUR-05 | Not started
PH-12 | Config | Add NEXT_PUBLIC_POSTHOG_KEY to .env.example | Project token for NCLEX-Nursia (595036). Public by design, like the GA4 and Meta pixel ids already there | NUR-05 | Not started
PH-13 | Config | Gate on the key, not on NODE_ENV | Unlike the other three tags. PostHog is the system of record; not seeing events in development is how instrumentation ships broken | NUR-05 | Not started
PH-14 | Performance | Land NUR-21 (Clarity off beforeInteractive) first | Buys budget headroom before a fourth script is added to the same pages | NUR-21 | Not started
PH-15 | Performance | Measure p75 LCP for 7 days, compare to baseline | HARD GATE. A regression past +100ms reverts the ticket (DOD-5) | NUR-22 | Not started

## PostHog dashboard
PostHog dashboard — Growth: channel to activation
Project NCLEX-Nursia (595036). Eleven tiles. Tiles 6 and 10 need no new instrumentation — build those first so the dashboard exists and carries real data while the rest fills in.
# | Tile | Insight type | Definition | Blocked on | Status | Insight URL
1 | Channel funnel | Funnel | $pageview > question_answered > registration_completed > activated > practice_session_completed, breakdown by utm_source | App contract | Not started
2 | Activation rate by channel | Trends (formula) | activated / registration_completed, weekly, by initial_utm_source. This is DOD-1's surface | App contract | Not started
3 | High-intent rate by channel | Trends (formula) | practice_session_completed / activated | App contract | Not started
4 | Landing page performance | Trends | $pageview by src — which creative cluster converts | NUR-05 | Not started
5 | Registration by method | Trends | registration_completed broken down by method (email/google/phone) | App contract | Not started
6 | Login health | Funnel | login_viewed > login_completed. Currently 101 > 1 | READY NOW | Not started
7 | Onboarding step drop-off | Funnel | onboarding_step_viewed by step_index, then onboarding_completed | NUR-16 | Not started
8 | Time to activation | Funnel (time to convert) | Median hours registration_completed > activated | App contract | Not started
9 | Paywall rejection | Funnel | subscription_page_viewed > purchase, paywall_dismissed as the leak | NUR-18 | Not started
10 | Core Web Vitals by page | Web vitals | p75 LCP / INP / CLS per URL. DOD-5 enforcement tile | READY NOW | Not started
11 | Activated-user retention | Retention | Cohort on activated, returning on practice_session_completed, weekly | App contract | Not started

## Performance budget
Performance budget — the constraint on every ticket
Baseline p75 from PostHog $web_vitals, 30 days to 11 Sep 2026 (312 events, 17 people). Google thresholds: LCP good ≤2500ms / poor >4000ms, CLS good ≤0.10, INP good ≤200ms.
Surface | Metric | Budget | Baseline p75 | Enforcement | Status | Re-measured
Paid landing pages /lp/* | LCP | ≤ 2500 |  | Blocks release of any LP change | Not started
Paid landing pages /lp/* | CLS | ≤ 0.10 |  | Blocks release | Not started
app.nursia.io/ | LCP | ≤ 2500 | 4461 | Remediation ticket, not a sprint blocker | Not started
app.nursia.io/ | CLS | ≤ 0.10 | 0.163 | Remediation ticket | Not started
app.nursia.io/ngn-onboarding | LCP | ≤ 2500 | 4236 | Remediation | Not started
app.nursia.io/qbank | LCP | ≤ 2500 | 3908 | Remediation | Not started
app.nursia.io/profile | LCP | ≤ 2500 | 3399 | Remediation | Not started
app.nursia.io/login | LCP | ≤ 2500 | 3394 | Remediation | Not started
app.nursia.io/flashcards | LCP | ≤ 2500 | 2957 | Remediation | Not started
app.nursia.io/analytics | LCP | ≤ 2500 | 1784 | Passing — hold it | Not started
Every surface | INP | ≤ 200 | 66 | Passing — hold it | Not started
Any analytics ticket | Delta LCP p75 | ≤ +100 |  | HARD GATE (DOD-5). Ship reverts if breached | Not started
Clarity tag (layout.tsx:138) | Script strategy | afterInteractive |  | Currently beforeInteractive — executes ahead of hydration. NUR-21 | Not started
Tag management | GTM | REJECTED |  | Adds a loader in front of existing tags; one blocked container kills all measurement at once, threatening DOD-1 and DOD-3. See PRD | Decided

## App contract
app.nursia.io — instrumentation contract
Not our repository. Twelve of twenty-four sprint tickets depend on this team. C-00 is a security fix and does not wait; C-01 to C-07 block activation and high-intent measurement entirely.
ID | Requirement | Detail | Severity | Status | Owner
C-00 | Strip auth fragments before capture | Supabase puts access/refresh/provider tokens in the URL fragment; PostHog stores them. 49 events affected | SECURITY | Not started
C-01 | Accept inbound attribution params on first load | Read utm_*, gclid, gbraid, wbraid, fbclid, src from the landing URL | Blocker | Not started
C-02 | Persist them as first-touch person properties | initial_utm_*. First touch wins, never overwritten | Blocker | Not started
C-03 | Mint _fbc from fbclid if absent | Format: fb.1.<timestamp>.<fbclid> | Blocker | Not started
C-04 | Emit registration_completed | THE TARGET EVENT. method + attribution. PostHog, GA4, Meta CompleteRegistration | Blocker | Not started
C-05 | Emit activated at 5th cumulative question | Once per person ever, server-authoritative. Needs question_answered first | Blocker | Not started
C-06 | Emit practice_session_completed | session_type = drill ¦ exam, plus score and duration | Blocker | Not started
C-07 | Adopt the shared event_id scheme | Same id to pixel and CAPI, or dedup fails and DOD-4 cannot pass | Blocker | Not started
C-08 | Emit purchase with value and currency | Required for ROAS by channel. Must carry the shared event_id so Meta and Ads can dedupe against it | Blocker | Not started
C-08b | Expose purchase to the Ads upload job | Purchase + stored gclid/gbraid/wbraid + timestamp, readable server-side for Offline Conversion Import | Blocker | Not started
C-09 | Add step_index to onboarding events | Else the onboarding funnel is unreadable | High | Not started
C-10 | Add login_failed with a reason | 101 login_viewed to 1 login_completed is currently unexplainable | High | Not started
C-11 | Confirm the PostHog project matches | Must be 595036 or the funnel splits across projects | High | Not started
C-12 | Remediate app entry LCP | p75 4461ms against a 2500ms budget on the page every paid click reaches | Medium | Not started
C-13 | Agree a shared staging test plan | Both sides verify before either ships | Medium | Not started